## Estimate
Estimate Detail
|  | TOTAL TIME: |  | 1734 | [6 empty] | Notes
© 2016, Aperia, Inc.
Estimate Detail
Project Name: |  |  |  |  | Estimator:
Date: |  |  |  |  | Notes:
Work Estimation Details |  | Spec | UI Des | Tech Des | Coding | TC | Testing | Promotion | PM | DO NOT
Project / Ticket | Feature | 20% | 15% | 15% | 1 | 40% | 40% | 5% | 15%
Ticket 1 | Feature 1 | 20 | 15 | 15 | 100 | 40 | 40 | 5 | 15
| Feature 2 | 25 | 20 | 15 | 150 | 40 | 40 | 10 | 15 |  | Time | Workgroup
| Feature 3 | 25 | 20 | 15 | 250 | 45 | 40 | 10 | 15 |  | 124 | Spec
| Feature 4 | 14 | 10 | 15 | 200 | 45 | 40 | 10 | 15 |  | 95 | UI Des
| Feature 5 | 20 | 15 | 15 | 50 | 40 | 40 | 5 | 15 |  | 90 | Tech Des
| Feature 6 | 20 | 15 | 15 | 50 | 40 | 40 | 5 | 15 |  | 800 | Coding
[11 empty] | 250 | TC
[11 empty] | 240 | Testing
[11 empty] | 45 | Promotion
[11 empty] | 90 | PM
Note on C10: 1. Work with client to collect requirement. Out: MOM 2. Discuss with Dev to get solutions. Out: MOM 3. Update all needed requirement to spec by UC. Out: UC Spec 4. Q%A with Client. OUT: Email 5. Q&A with Dev, Tester. OUT: Email 6. Review TC of QC. OUT: Review result 7. Update change from client/dev to spec 8. Review Spec by expert 9. Write user guile
Note on D10: 1. Design screenshot 2. Design for responsive in Mobile 3. Design for Ipad
Note on E10: 1. Architecture design 2. Component Design 3. Classes design 4. Data base design 5. Database worflow 6. Sequence diagrame for complex feature
Note on F10: 1. Dev analyze requirement. Q&A 2. Implement html, css, code behind, sql, database 3. Implement to support multi browser 4. Implement support responsive in mobile 5. Implement to support resposive in Ipad 6. Unit test 7. Run TC of QC 8. Fix bugs 9. Review code by expert.
Note on G10: 1. Write TC 2. Write Automation test
Note on H10: 1. Execute TC on QA 2. Execute TC on Pro 3. Execute TC in 5 desktop brower 4. Execute TC in 5 mobile brower 5. Verify bug 6. Regression Test 7. Run automation Test
Note on I10: 1. Build package 2. Verify package after deploy
Note on J10: 1. Time for team planning, weekly meeting, improvement meeting 2. Time to do weekly report 3. Quality assurance 4. Discussion to resolve problem